## Sheet1
|  | Project Name | Mahfil App testing
|  | Test case Author | Sanjida Akter
|  | Test Environment | Android Device
|  | Test Execution Date | 2024-06-01
|  | Test Case Reviewer | Steadfast IT
Module | User Authentication
Test case step | Test Scenario | Input Data | Expected Results | Actual Results | Execution Status | Bug Priority
1 | Verify Sign Up functionality | Continue with google | The user should be successfully signed up and welcome to home page. | Signed up | Pass
2 |  | Continue with email |  | Signed up | Pass
3 |  | Log in another way |  | Signed up | Pass
4 | Verify Log out & login |  | The user should be logged out & Login in the same account | Log out But cannot log in into the same account | Reject | High
5 | Password recovery functionality |  | Password should berecovered successfully. | No option found | Reject | High
Module | Content Categories
1 | Verify Categories Accessibility |  | •Each category should be clickable. •Clicking on a main category should navigate to the respective category page. | All Categories are accessable & navigate to the respective page | Pass
2 | Verify Content Organization in Categories |  | •Content should be organized logically and consistently. •Each category should have a clear and correct title. | All Categories are organized & they have correct title. | Pass
3 | Verify Accessibility Features | Keyboard navigation | •All content should be accessible via screen reader. •Keyboard navigation should allow access. | Navigated and accessed.
Module | Video Streaming
1 | Verify Video Loading Time | Selected video | The video should start playing within a reasonable time frame | The video started playing within a reasonable time.(1 sec) | Pass
2 | Verify Smooth Playback |  | video quality should remain consistent without any buffering | Video quality remain consistent without any buffering when strong internet connection | Pass
3 | Verify Pause and Play Function |  | The video should pause/play immediately when the "Pause"/"Play" button is clicked. | The video pause/play immediately when the "Pause"/"Play" button is clicked. | Pass
4 | Verify Autoplay Functionality |  | The next video in the queue should start playing automatically after the current video ends. | The next video in the queue startes playing automatically. | Pass
5 | Verify Full-Screen Functionality |  | The video should enter/exit full-screen mode when the "Full-Screen"/"Exit full screen" button is clicked. | The video enter/exit full-screen mode correctly. | Pass
6 | Verify Audio Controls | Audio settings | The video should mute and unmute correctly when the respective buttons are clicked. | The video muted and unmuted correctly. | Pass
7 | Verify 10s earlier Functionality | time stamp | The video should 10 sec earlier from remain when the respective buttons are clicked. | Video 10 sec earlier from current status. | Pass
Module | Unique Video Content
1 | Verify Uniqueness of Content | Scroll vertically | •The new video should have a unique •Not a duplicate of any existing video. | Thevideos are unique & Not a duplicate of any existing video. | Pass
2 | Verify similar to Islamic Principle |  | Islamic principles should be approved | Islamic Content | Pass
Module | Download Functionality
1 | Verify Download Functionality | Only Available on paid version
Module | Search and Filters
1 | Verify Search Function for Single Content | Search item: "Ramadan" | Search results should be relevant | Relevent result | Pass
2 | Verify Filter by Category | Selected Category: "Tilaoat" | No content from other categories should be displayed. | Relevent catagory result | Pass
3 | Verify that filters | Search item: "Ramadan" | Search results should be by category, date, or popularity | Given search result are random | Reject | Low
Module | User Interaction
1 | Verify Like Functionality | Selected video/"Like" button | The like count for the video should increment by one. | Count incremented | Pass
2 | Verify Comment Functionality | Selected video Comment Text: "Good video!" | The comment should appear immediately under the video. | The comment appeared | Pass
3 | Verify Share Functionality | Selected video Share Platform: Messenger | The share on Msessenger should done | Shared on messenger | Pass
4 | Verify Notification Functionality |  | •The notification should included •The user should receive a notification indicating number | The notification included but number does not show up | Reject | Medium
Module | Performance Testing
1 | Video Playback Performance | Network:4G connection | •Video should start playing within 2 seconds of clicking the button .•There should be no buffering interruptions during playback. | Start playing time is good and no buffering in high speed connection | Pass
2 | Video Loading Delay |  | •Video thumbnail and title should load within 3 seconds .•Playback should remain smooth with minimal buffering. | Loaded instantly and smooth playback | Pass
3 | Verify App Responsiveness During Video Playback | User Actions: Pause, play, seek, and volume change during playback | The app should respond instantly to every actions. | The app responded instantly | Pass
4 | Download speed | Not appplicable